## README
Last Update | 2018-10-17
Author | Aaroh Mankad, Andrew Pirelli, Derek Sayler, Josh Madrid, Justin Schopick
Email | amank001@ucr.edu, apire001@ucr.edu, dsayl001@ucr.edu, jmadr004@ucr.edu, jscho004@ucr.edu
Description | This is the SCRUM Board for the Trips project
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | User Account | As a user I would like to create/delete an account for the travel app. So that I can log in and out and have my trip information tied to my account. Email and password registration. Must encrypt password for security (bcrypt) | 5 | 1 | Split between front-end and back-end
2 | Functionality | As a user I would like to add trips to a list. I would like to have different list types for places i've visited and for places I would like to visit. I would also like to view lists presented by the app for places to go and see. | 4 | 2 | Split between front-end and back-end
3 | Modifying | as a user i would like to modify my saved trips. Return all trips per user. Change trips (delete items from trip list). Show shortest route between stops | 4 | 3 | Split between front-end and back-end
4 | Planning | as a user I would like to be able to plan my trips using locations on google maps. Add multiple events to a trip. | 8 | 4 | Split between front-end and back-end
5 | Explorations | As a user I would like to be able to look up information about locations I am interested in. Use geolocation or entered locations. Look up information from google maps/trips api | 5 | 5 | Split between front-end and back-end
6 | Recommendations | As a user I would like recommendations for nearby/popular places. Recommendations will be populated by Google Maps API. Otherwise, recommend locations that friends have gone on trips to that location | 4 | 6 | Split between front-end and back-end
7 | Friends | as a user i'd like to have a list of "friends", and I can see their trips in a feed. Be able to add friends to user profile. Be able to search for user profile/ on their profile see their information and trips | 6 | 7 | Split between front-end and back-end
8 | contacts | As a user I would like to share my trips with other users. Have share button that can send a link to another user. | 3 | 8 | Split between front-end and back-end
9 | information | As a user I would like to look up a city and get information about that city. This would include tourist locations and info about that locations. Food venues to include menus. Events within the city I am visiting | 4 | 9 | Split between front-end and back-end
10 | reservation | As a user I would like to view my reservation information for past and upcoming trips. Building on the ability to fetch trips per user, include filters for date, location, etc | 2 | 10 | Split between front-end and back-end
11 | day planner | As a user I would like to have a planner to keep track of my daily plans while I am on my trip. Also I might want to plan just one day to go to places within a days drive near me | 5 | 11 | Split between front-end and back-end
| Total |  | 50

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
|  | Justin Schopick | Task 1: Be able to create a user in API (Aaroh Mankad)
|  | Derek Sayler | Task 2: Build app Database for user info (Derek Sayler)
| Task 3: Day planner (Joshua Madrid) | Aaroh Mankad
|  | Joshua Madrid | Task 4: Create a User login interface (Justin Schopick)
|  | Andrew Pirelli | Task 5: Hashing the Passwords (Aaroh Mankad)
|  | Derek Sayler | Task 6: Query Google maps API (Andrew Pirelli)
Task 7: Display details of attractions from Google API (Andrew Pirelli)
Task 8: Populate Photos (Aaroh Mankad)
Task 9: Create Trip in UI
Task 10: Build database to save for trips and attractions (Derek Sayler)

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Aaroh Mankad | Task 1 create user in the API
1 | Aaroh Mankad | Task 4 create a user login interface
1 | Aaroh Mankad | Task 2 Build app Database for user info
1 | Aaroh Mankad | Task 5 Hasing the Passwords
2 | Derek Sayler | Task 6: Query Google maps API

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 50 | 0 | 0 | 50 | 50
1 | 50 | 0 | 0 | 50 | 50
2 | 50 | 5 | 10 | 45 | 15
3 | 50 | 15 | 20 | 35 | 20
4 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0